## Cover
Team LZJCO
Prepared By:
Jean-Cedrik Dorelas
Louay Dridi
Constance Fleury
Zaree Choudhry Hameed
Octavian Mihai

## Product Backlog
Issue # | User story | Associated Tasks | Story points associated to a US | Priority | Risk (High, Medium, Low) | Responsible | Due date
1 | User will see Registration/Login Page upon opening the website | -Create the UI for Login and Register Page. -Make sure passwords match. -Have a "Or Login?/ Or Register" buttons to switch from login/registers -add a show password button | 4 | HIGH | HIGH: If user can't create his profile, he will not be able to access anything in the website | Frontend Zaree Cedric | 2026-02-02
2 | User will be able to Register and Login | -Add functionality to save user data in a database -Add functionality to retrieve user data from the database | 5 | HIGH | HIGH: If user can't create his profile, he will not be able to access anything in the website | Backend Louay/Cedric | 2026-02-02
3 | User will be able to manage his profile | -Create Profile Management page -Add functions to edit: -User Name -User Password -Allergies -Preferences | 6 | MEDIUM | MEDIUM | Frontend: Constance Backend: Octavian Louay | 2026-02-05
4 | User will see Home Page Right after Logging in | -Create Home Page | 2 | LOW | LOW | Frontend: Constance | 2026-01-30
17
5 | User will be able to click on recipes to search for recipes | -Load all recipes and create a search bar wit hfilter checkboxes. -only show the recipes that fit the fitler | 4 | MEDIUM | LOW: if user can't filter he can still see all recipes | Frontend and Backend: Cedric | 2026-02-25
6 | User will be able to Create recipes | -Create the UI for Creating recipe. Should be the same as the edit version -Save all of this information in the database | 6 | HIGH | HIGH: If user can't create recipes. he can't see or edit any of them | Fronted: Zaree Backend: Louay | 2026-02-20
7 | User will be able to edit and delete recipes | -fload all recipes and fill all the page with them -Create the UI for editing a specific recipe. should be the same as creating one -save the changes on the same node in the database | 5 | HIGH/MEDIUM | MEDIUM: user will not be able to do any changes in any recipe but they will still exist | Fronted: Octavian Backend: Constance | 2026-02-25
15
8 | User will be able to see his weekly mean plan | -Deisng the UI for the weekkly meal plan -Have the ability to go to the next/previous week -Have the week start at Sunday and end on Saturday -Upon clicking on the day of the week, Buttons to add, eidt and remove meals from the day will appear | 4 | HIGH | HIGH: If there's no way to display recipes in a weekly manner, there is also no way to create/edit/remove recipes | Frontend: Octavian | 2026-03-18
9 | User will be able to assign meals to the day of the week and its type (breakfast/lunch/dinner/snack) | -Upon clicking on the add recipe button for a day, get all recipes from the database and assign it to that day -Meals should also get a type that will be assigned to them (breakfast/lunch/dinner/snack) | 6 | HIGH | HIGH: If there is no recipe added, then it is impossible to edit/remove them | Constance | 2026-03-20
10 | User will be able to edit or remove meals from a day | -Upon clicking on the remove/edit button, prompt the user to select which recipe of that day they want to remove/edit -Remove/edit that specific meal | 5 | MEDIUM | MEDIUM: User cannot modify weekly plan | Cedric | 2026-03-21
11 | System will prevent duplicate meal assignments in the same week | -Implement duplicate validation logic -Check if recipe already exists in same week -Prevent overwrite -Display error message -Write Unit Test for the isDuplicate() Method | 3 | LOW | LOW: It does not affect ay other task | Cedric Constance | 2026-03-21
12 | System will automatically test every push and pull request made | -Write test cases -Validate CRUD operations -Test duplicate prevention -Perform integration testing | 5 | LOW | LOW: It does not affect any other task | Zaree | 2026-03-21
13 | User will be able to ask for a weekly plan given certain ingrediants | -Create API key for LLM -Initialize Firebase Functions - Manage the LLM-firebase functions pipeline | 4 | LOW | LOW: It does not affect any other task | Louay | 2026-03-21
14 | user will be able to track his daily calories on the calendar | -Update infroamtion sent to firebase to include calories -Include daily calorie limit in the user's profile preferences -Update recipe UI to include calories | 4 | LOW | LOW: It does not affect any other task | Louay | 2026-03-27
15 | User interface styling will be modular and easier to maintain | -Separate styling from WeeklyPlanner.html into WeeklyPlanner.css -Improve maintainability and readability of UI code -Allow easier future UI updates | 2 | LOW | LOW: It does not affect ay other task | Constance | 2026-03-27
16 |  |  | 33
17 | Code/Peer Review | -ensure code quality, correctness, and adherence to project standards -Use a static analysis tool to find 5 bugs and fix them (examples in sprint 4 instrcutions) | 4 | MEDIUM | HIGH: thiss directly affects code quality and therefore user experience | Louay Constance Cedric Octavian | 2026-04-09
12 | System will automatically test every push and pull request made | -Write unit test for all code -write at least 2 acceptance tests for all user stories | 5 | LOW | LOW: It does not affect any other task | Zaree | 2026-04-09
Story Points per sprint
[9 empty] | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
[8 empty] | Louay | 4 | 3 | 8 | 1 | 16
[8 empty] | Constance | 3 | 3 | 7 | 1 | 14
[8 empty] | Octav | 4 | 3 | 6 | 1 | 14
[8 empty] | Cedric | 3 | 3 | 7 | 1 | 14
[8 empty] | Zaree | 3 | 3 | 5 | 5 | 16
[9 empty] | 17 | 15 | 33 | 9